## Risk Register
Helios Energy Analytics – Cybersecurity Risk Register
Portfolio artefact demonstrating risk identification, scoring, ownership, treatment planning and evidence traceability for the Azure Cloud Governance case study.
Document Owner | Kevin Wadsworth | Version | 1.1 | Status | Draft for portfolio evidence | Last Updated | 2026-04-29
Framework Alignment | ISO 27001 / NIST CSF | Project | Helios Azure Cloud Governance | Review Cycle | Monthly | Classification | Internal / Portfolio
Risk ID | Risk Title | Asset / Process | Risk Category | Threat Event | Vulnerability / Cause | Business Impact | Likelihood (1-5) | Impact (1-5) | Inherent Score | Risk Rating | Existing Controls | Treatment Plan | Risk Owner | Target Date | Status | Residual Score | Evidence Link | Notes
R-001 | Public storage exposure | Azure Storage Account | Data Protection | Unauthorised disclosure of data | Public blob access enabled or misconfigured container permissions | Potential disclosure of sensitive information, regulatory exposure and reputational damage | 4 | 5 | 20 | High | Azure Policy; storage configuration review; Resource Graph query | Disable public access, verify container permissions and monitor for drift | Cloud Platform Owner | 2026-05-15 | Open | 8 | azure-governance-evidence.html | High-priority evidence of cloud exposure risk.
R-002 | Unrestricted network access | Network Security Group | Network Security | Brute-force or unauthorised inbound access | Inbound rule allows broad access from the internet | Increased attack surface and potential compromise of workloads | 4 | 5 | 20 | High | NSG rules; management access review | Restrict inbound access to trusted ranges and document approved management paths | Security Owner | 2026-05-20 | Open | 10 | azure-governance-evidence.html | Demonstrates risk-based network control thinking.
R-003 | Deployment outside approved region | Azure Resource Deployment | Compliance / Data Residency | Resource created outside approved geography | Allowed location control not followed or exception not approved | Potential data residency or governance breach and inconsistent control enforcement | 3 | 4 | 12 | Medium | Allowed locations policy; subscription-level governance baseline | Restrict deployments to UK South / UK West; use formal exception where justified | Cloud Governance Owner | 2026-05-10 | In Progress | 6 | azure-governance-evidence.html | Shows regional governance and policy enforcement.
R-004 | Missing resource ownership tag | Azure Resource Inventory | Governance / Accountability | Delayed remediation during incident or audit | Owner tag missing or inconsistent across resources | Weak accountability, poor cost ownership and slower remediation | 3 | 3 | 9 | Medium | Mandatory Owner tag policy; resource inventory review | Enforce Owner tag, remediate non-compliant resources and review exceptions | Resource Owner | 2026-05-05 | In Progress | 4 | azure-governance-evidence.html | Useful for showing GRC operating model.
R-005 | Insufficient compliance evidence | Monitoring & Evidence Repository | Audit / Assurance | Inability to prove control operation during review | Evidence capture not consistent or not retained centrally | Reduced audit readiness and limited assurance over control effectiveness | 2 | 4 | 8 | Medium | Azure Storage evidence repository; screenshots; policy outputs | Automate evidence capture using scheduled reports and define retention period | GRC Owner | 2026-05-30 | Open | 5 | azure-governance-evidence.html | Shows evidence-based compliance mindset.
R-006 | Manual compliance monitoring | Compliance Monitoring Process | Operational Resilience | Governance drift goes undetected | Manual reviews are inconsistent and not time-bound | Non-compliance could persist without timely detection | 3 | 4 | 12 | Medium | Timer-triggered Azure Function; Resource Graph queries | Schedule recurring checks and route exceptions into risk review process | GRC Owner | 2026-06-15 | In Progress | 6 | azure-governance-evidence.html | Supports automation capability.
R-007 | Privileged access not reviewed | Azure RBAC / IAM | Access Control | Excessive privilege or orphaned access remains active | Role assignments not reviewed regularly | Unauthorised changes or elevated access beyond business need | 3 | 5 | 15 | Medium | RBAC; managed identity; least privilege review | Perform quarterly access review and remove unused elevated access | Security Owner | 2026-06-30 | Planned | 9 | azure-governance-evidence.html | Relevant for ISO access control mapping.

## Document Info
Document | Helios Energy Analytics – Cybersecurity Risk Register
Purpose | Portfolio artefact demonstrating risk identification, scoring, ownership, treatment planning and evidence traceability for the Azure Cloud Governance case study.
Owner | Kevin Wadsworth
Version | 1.2
Status | Draft for portfolio evidence
Last Updated | 2026-04-29
Framework Alignment | ISO 27001 / NIST CSF
Project | Helios Azure Cloud Governance
Review Cycle | Monthly
Classification | Internal / Portfolio

## Scoring Guide
Score Area | Scale | Description
Likelihood | 1 | Rare / unlikely
Likelihood | 2 | Possible but not expected
Likelihood | 3 | Reasonably possible
Likelihood | 4 | Likely
Likelihood | 5 | Almost certain
Impact | 1 | Minor operational impact
Impact | 2 | Limited business impact
Impact | 3 | Moderate business impact
Impact | 4 | Major business, compliance or operational impact
Impact | 5 | Severe regulatory, financial or reputational impact
Risk Rating | Low | 1–7
Risk Rating | Medium | 8–15
Risk Rating | High | 16–25